## Project Timeline
2 | YOUR PROJECT
TIMELINE
PROJECT DETAILS
| DATE | MILESTONE | POSITION | BASELINE
| 2015-08-31 | Project Start | -5 | 1
| 2015-09-07 | Team Meeting; 1st homework started | 5 | 1
| 2015-09-14 | Homework #1 Due! | 10 | 1
| 2015-09-21 | Homework #2 Due | 15 | 1
| 2015-09-28 | Homework #3 Due | 20 | 1
| 2015-10-05 | UML diags final; proj plan final | 5 | 1
| 2015-10-12 | Database design draft | 10 | 1
| 2015-10-19 | Mid-semester peer reviews due | 15 | 1
| 2015-10-26 | Draft IT requirements, including network design | 5 | 1
| 2015-11-02 | Homework #4 Due | 10 | 1
| 2015-11-09 | First Demo of Prototype | -5 | 1
| 2015-11-16 | User Validation & Test plan finalized | 10 | 1
| 2015-11-23 | Client Visit | -5 | 1
| 2015-11-30 | Draft Documentation | 5 | 1
| 2015-12-07 | Paper Due - Final Documentation | 10 | 1
| 2015-12-14 | FINAL PRESENTATION! | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2015-08-31 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2015-08-31 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2015-08-31 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2015-09-01 | Team Meeting | First Team Meeting. Break down Homework 1 into 4 manageable sections. As a group decide which questions need to be asked of the client at the next class. Think about project from all 3 majors point of view. Review project description and decide the user requirements. Compile into an executive summary which can be edited after meeting with client. Choose next meeting. | All | Had first team meeting and worked on HW#1 inclduing intial setup of project plan and brainstorming for project. Sent into PM for feedback.
2015-09-04 | Team Meeting | Second Team Meeting. Work on Project Plan to ensure work is completed in timely fashion. Create possible deadlines for future tasks. Create two UMLs based on the two different scenerios discussed previously. IS student creates status update for the week. | All | Received feedback from PM and created appropriate changes to HW#1
2015-09-07 | Team Meeting; 1st homework started | Have met at least once by the end of the day on 9/7; have started Homework #1 minimally - add more items to this project plan in the empty lines below and have altered this line to be something more meaninful than my babble… | All
2015-09-14 | Homework #1 Due! | Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
2015-09-15 | Team Meeting; Begin planning ER diagram | Discuss what went well with the process for Homework 1. Dicuss the answers that the client gave us from class and adjust user requirements, UML documents, and project plan as needed. Begin thinking about which tables need to be created for database. | CS (creators) IT and IS (contributors) | Decided not to meet on this day and just meet on Friday 9/18.
2015-09-18 | Team Meeting; Work on Homework #2 | Finalize database tables. Create Entity-Relationship diagram. Discuss different design ideas and choose the most effective one. Develop documentation for the ER diagram. IS student creates status update for the week. | CS (creators) IT and IS (contributors) | Discussed what went well on Homework 1 (completed all goals during each meeting, had good communication with project manager). Started on homework #2 by creating the ERD. Sent to Project Manager for review. Edited and revised Hw#1. Created weekly status update.
2015-09-21 | Homework #2 Due | E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams. | All | Homework #2 given an extention by Project Manager to Friday 9/25. Homework #3 given extension to October 25th. Addressed credit hours issue. Decided on goals for 9/22 meeting.
2015-09-22 | Team Meeting; Begin working on database design | Discuss what went well with the process for Homework 2. Update previous documents as needed. Discuss design for GUI/interface. Review design principles. CS students begin work on prototype of database. | IT and IS (Wireframing) CS (database) | Updated Project Plan. Finished updating user requirements. Created additional document describeing ER diagram. Finalized ERD. IT student begame working on IT Plan. Going to start on Homework #3 on Friday 9/25.
2015-09-25 | Team Meeting; Work on Homework #3 | Create 5 wireframes/mockups that depict design discussed in previous team meeting. Confirm with all team memebers this is the best design. CS students continue work on protoype of database. IS student creates status update for the week. | IT and IS (Wireframing) CS (database) | Wrote create statements for tables in Database prototype. Started wireframe mockups. Continued work on IT plan. Updated Project Plan. Edited ERD.
2015-09-28 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface. | All | Just to reiterate this due date has been pushed back to Friday 10/2. In addition Project Manager informed us that Major Concetrations are out of scope.
2015-09-29 | Team Meeting | Discuss what went well with the process for Homework 3. Update previous documents as needed. CS students continue work on protoype of databases. Confirm securirty permissions. IT and IS students finalize UML diagrams. | Mostly CS students IT and IS (UML) | We as a group decided CAS was out of scope but will document it as a future opportunity. Finished wireframes. Updated project plan. Came up with activities and sent to Project Manager.
2015-10-02 | Team Meeting | NEW: HOMEWORK 3 DUE DATE. CS students continue work on prototype of database. Meet with SME as needed. Begin creating documentation for the database. IS student creates status update for the week. | Mostly CS students | Finished up final wireframes after feedback from Project Manager. Decided on plan for next week. Updated Project Plan and status report.
2015-10-05 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams | All | Checked in PM to make sure project is going well.
2015-10-06 | Team Meeting | CS students continue work on prototype of database. Discuss stored procedures and whether or not they will be needed. Continue documenting. | Mostly CS students | Set of local copy of postgres and ran create statements to make sure they work. Worked on GUI design on paper. Jon worked on ROI calculations.
2015-10-09 | Team Meeting | CS students continue work on prototype database. CS students begin work on GUI. IS and IT students help debug as needed and work on final paper. IS student creates status update for the week. | All | Started researching new technologies such as Node.js and Express.js. Finalized some design details and updated ER diagram.
2015-10-12 | Database design draft | Draft database design | CS Students | Checked in PM to make sure project in progressing accordingly.
2015-10-13 | Team Meeting | CS students are still working on database and GUI. IS/IT students review work of CS students and continue paper. | All | Kevin created 3 servers, 1 for database, 1 for application, and 1 for backup. Decided on majors that are going to be used for testing and collected data accordingly. Assigned "fake" credit hours to data.
2015-10-16 | Team Meeting | CS students are still working on database and GUI. IS/IT students review work of CS students and continue paper. IS student creates status update for the week. Discuss what has gone well and what hasn't gone well as a team so far. Address issues as needed before peer reviews. | All | Did not meet. Midsemester break. Weon worked on GUI. Kevin continued work on servers.
2015-10-19 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews | All | Checked in PM to make sure everything is going well. Asked for Kevin to send IT documents for initial reveiw.
2015-10-20 | Team Meeting | CS students still work on database and GUI. IS/IT students try using GUI and see what needs to be changed. | All | Cancelled meeting because still waiting on client access to servers.
2015-10-23 | Team Meeting | CS students still work on database and GUI. IS/IT students try using GUI and see what needs to be changed for easier usability. Discuss disabilities that might need special consideration for GUI such as colorblindness. IS student creates status update for the week. | All | Charlie worked on selecting and cleaning up the small portion of data we will need for testing and creating csv files. Jaime looked into postgres commands for the server to create the database and insert data. Weon continued work on GUI. Kevin working on getting NGINX onto the application server. Jon working up uploading database dump file to server. Updated documentation.
2015-10-26 | Draft IT requirements, including network design | IT student discusses IT needs with CS and IS students. Begin drafting IT plan. | Mostly IT student
2015-10-26 | Team Meeting | CS students complete initial database prototype and meet with SME to discuss. CS students also continue work on GUI.IT student continues work on IT plan. IS student continues work on paper. | All | Jaime and Charlies created database and tables on database server. Kevin showed everyone how he setup servers. Weon continued wrok on GUI. Jon began research on Node.js API.
2015-10-30 | Team Meeting | CS students finish database prototype and documentation. IT student continues work on IT plan. IS student continues work on paper and status update for the week. | All | Jaime and Charlie created SQL files to load data into database. Kevin changed backup server into test server to test API on. Weon continued work on GUI. Jon continued learning Node js.
2015-11-02 | Homework #4 Due | Database prototype complete | CS students
2015-11-02 | Team Meeting | CS students finish work on GUI to review with whole group. IT student finished IT plan. | All | Database has enough test data in order to do simple functionality. Jon, Jaime, Charlie, and Kevin continue work on API.
2015-11-04 | Team Meeting | Create Node js API. | All | Had an additional meeting because we are having trouble creating API. Tried to connect to server but had a lot of errors. Weon continued working on GUI.
2015-11-06 | Team Meeting | Group meets to practice demo. | All | Still working on API and still having trouble. We are pushing off practicing demo to Sunday.
2015-11-08 | Team Meeting | Finish API and practice demo. | All | Trying to get API working and practice demoing.
2015-11-09 | First Demo of Prototype | Complete project prototype first-pass demo ready | All
2015-11-09 | Team Meeting | Continue Node.js API work. | All | Met with SMEs to try and get API workng. Server having issues. Weon still worked on front end. Jaime and Charlie cotinued the API. Kevin and Jon worked on fixing up documentation.
2015-11-13 | Team Meeting | Try and get Node.js API working. | All | Meeting cancelled because of school lockdown. Continued individual work. Decided to get rid of database server in order to resolve connection issues with API and server.
2015-11-16 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented
2015-11-16 | Team Meeting | Test API | All | Finally got API working on application server when database was moved to that server. Jaime and Charlie sat down with Weon to go over all queries that need to be made in order for front end to function correctly. Jon and Kevin worked on documentation and setting up paper. Weon changed framework on front end from React to angular.
2015-11-20 | Team Meeting | Connect Database and Front End | All | Charlie continued writing post and gets for API. Weon worked on making sessions restorable. Jon organized all current documentation for final paper. Kevin still working on documentation. Jaime updated ERD and ERD documentation along with project plan.
2015-11-23 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented |  | Cancelled. No meetings or class during Thanksgiving week.
2015-11-30 | Draft Documentation | All documentation required for the project in Draft form
2015-11-20 | Team Meeting | API, Front end, and Paper work | All | Jon and Kevin worked on paper and documentatin. Charlie and Jaime continued working on API and cleaning up the datatbase. Weon worked on session storage, saving it and returning to it.
2015-12-04 | Team Meeting | API, Front end, and Paper work | All | Jon is still working on the paper. Kevin updated IT requirements. Weon worked on connected the front end and the back end. Charlie is still working on API JSON posts. Jaime changed some SQL queries in the API and the database structure slightly removing one column from Admins table.
2015-12-07 | Paper Due - Final Documentation | All documentation required for the project in FINAL form
2015-12-07 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All
2015-12-07 | Team Meeting | Start Work on Presentation | All | Charlie and Weon worked on finishing the logic for the report generated after the submit button. Jon continued work on final paper. Jaime edited the database and started work on final powerpoint. Kevin tried getting mail server up and running.
2015-12-11 | Team Meeting | Finish Everything! | All | Charlie wrote API logic for Admin capabilities. Weon synchronizing data from database for final report. Jon worked on final touches of the paper. Kevin still working on mail server. Jaime still working on final presentation.
2015-12-14 | FINAL PRESENTATION! | Git er dun! | All

## Week Class Sched - Fall2015
Week | Class Topics and Activities | Assignments Due | Class Format
8/31 | Introduction; Project case study; Project plan; |  | Group (HC2023)
Sections and Teams; Project overview
9/7 | NO CLASS: Labor Day
9/14 | Client Interview | Homework 1 due | Group (HC2023)
9/21 | SME visit | Team status report
Brown bag session
Homework 2 due
9/28 | Project Management and UML | Team status report | Group (HC2023)
Brown bag session
Homework 3 due
10/5 | Guest presentation: Alan Labouseur - database | Team status report | Group (HC2023)
Brown bag session
10/12 |  | Team status report | HC2023 available
|  | Brown bag session | if needed
10/19 | Networking | Team status report | Group (HC2023)
| Draft peer-reviews | Brown bag session
10/26 |  | Team status report
Brown bag session
11/2 |  | Team status report: Database | HC2023 available
|  | Homework 4 due | if needed
11/9 | Prototype 1st Demonstration | Rough draft demo presentations
11/16 | User Validation & Test Planning | Team status report | Group (HC2023)
Brown bag session
11/23 | Client visit | Team status report
Brown bag session
11/30 | SME visit | Team status report
| Draft documentation / paper | Brown bag session
12/7 | Final documentation / paper | Brown bag session
| Final peer-reviews | Project paper due
Peer evaluations due
12/14 | Project presentations | Project prototype due
Project presentations

## Weekly Status Reports
Status Report - HERBY, Kevin, Jamie, Weon, Charlie, and Jon
Date
RGY | Item | Description | Mitigation / Help needed | Date
Green | Homework #1 | Created Group.We created 2 UML's and filled out the Project plan and came up with questions. We also clearly documented the set of user requirements based on the information that we have received. |  | 8/31/2015-9/4/2015
Green | Homework #1 | Received feedback from Professor Algozzine. met on 9/8 and 9/11 to edit our work and submit our project. |  | 9/7-9/12
Green | User requirements | Met with the Client and asked questions. Then on 9/15 we updated our user requirements. |  | 9/14 and 9/15
Green | Homework 2, rough draft and weekly progress report due | We finished the rough Draft of our ERD, and submitted our weekly progress report. | We need help in getting and understanding exact credit hours for each class. We believe that it will be a huge issue in transfering credit hours. Also, How will the majors table transfer and seperate courses into core and elective credits. (Answered/Fixed) | 2015-09-21
Green | Homework #2 | Wrapped up Homework #2. Finished up Homework #2. We submitted the work and worked on the wireframe for homework #3. |  | 2015-09-25
Green | Homework #3 | We are continuously working on HW#3 (due October 2nd) and we have even started working on some of HW#4. The wireframing is going well and we are creating a very aesthetically and ergonomically pleasing UI for the user. | Would you like any documentation for the wireframes? If so, how would you like it presented? (answered) | 9/28/2015 (Class)
Green | Activity Diagram | We finished exerything on HW#3, but we could not complete activity diaigram because Project Manager never contacted us about which one to do. | We are waiting on the Project Director to tell us what Activity Diagram to create.(Answered) | 2015-10-02
Green | Homework #4 | We have started HW#4 and work is under way. We are continuously having our meetings and doing work. IT launched a windows virtual server to begin construction of the DB. As our team still waits to hear from the P.D. we have discusses how we would create many on the different activities on an activity Diagram, but we just need the go ahead on which A.D. to create. | Currently still waiting on the word from the Project Director for the go ahead on which Activity Diagram to create.(Answered/fixed) | 2015-10-05
Green | Homework #4 | We have been working on the database and we have also been cleaning, and fudging the data a little. We have also been working on the GUI. | We are having issues with the data being terrible, outdated, and it not making sense, so we are fudging it a little because our client isn't able to give us more accurate/cleaner data. | 2015-10-09
Green | Postgress | We keep working on the database and started working on the front end and back end of the program by downloaded node and express which is nodes framework. |  | 2015-10-19
Green | Foxify is growing | The 3 serevers are up! We have the DB sever, the front end (application server) and the backup server. We have downloaded node.js and express.js on the application server. we are also creating a dump file of the DB to throw into the DB server. | We are waiting for a responce from the project director in regards to pathways. We are having trouble using a dump file to transfer our database, so we have to type in our database into the DB server to recreate it.(Resolved) | 2015-10-23
Green | More Progress | We have continually been working on the front end and back end. The API has been very time consuming getting it to connect the front end and back end to gether. | We need help with the API. We have saught the help of other groups and the project director. We are continually working on everything, but we have shifted more of the focus on the API. | 2015-11-02
Green | Presentation | We have mad a lot of progress on both the front end and back end. The GUI is coming together very nicely and is mobile device compatible. The backend and DB are looking very god as well. | After seeking help of various professors, students, and other outside sources we are still having a diffucult time with our API. The code seems to be fine its just there is something not letting the API make the connection. We have tried many different things to get it to work, but still no connection. We are planning to meet with Chris Ahmed this week to see if he can help us solve our connection issues. | 2015-11-09
Green | Meeting and presentation | We did not meet on friday because we decided to cancel our meeting as the campus was on lock-down. Although we did not meet we have made progress with connection issues between the front end and back end with the API. We met with Chris Ahmed to help us fix some of the connection issues and also we sought help from Alan. | We have made an executive desicion to put the API and the DB on the Application server. We started fresh and re-installed postgres, because we believe that our issues stemed from not properly installing postgres on the DB server initially to meet our needs.Between the help from Chris Ahmed and Alan we have learned a lot and made progress with the connection. We have also had a greeat break through with the front end by not using react and anything react related. The framework was very time consuming to learn and was confusing. Instead we switched to angular.This will make course selection and filtration easier. | 2015-11-16
Green | no meeting with group or professor | After meeting a couple times in the previous week we decided not to meet on 11/23 because a few of the group members would already be traveling. We assigned roles for each person to work on during the week of vacation and we constatly talked and checked on each others status. | Our team telecommuted and discussed progress and each others assignments and goals for the week of break. Everyone made progress on what we were all working on and assigned. The week of the break was not a set back or a loss of time at all. Jon worked on the final paper.Kevin, worked on solidifying and editing the documentation for the paper. Jamie, worked on the database and some DB documentation. Charlie, worked on the API and the DB.Weon, kept on working on the front end and touched up on some documentation as well. | 2015-11-23
Green | Meeting with professor, status report and presentation or current work. Team meeting. | We are continually working on everything as a group and we are meeting to show what we all worked on over break and to move foreward. As we get closer to the wire we are all pushing foreward to finishing up and testing. | With much progress made over break we are meeting to help each other out and to move foreward to finishing up and then onto testing while we finish up the final documentation and brushing up the paper. | 2015-11-30
Green | Final Status update and Demo with no dry run of the final presentation. | As a group we have made a lot of progress in every relm of the project. We are wrapping up the Final paper, finishing up the logic with the call functions with the API. Connected to the front end and back end through the API. We are also putting finishing touched on the GUI to make it look as pretty as possible. | As a group we are sprinting to the finish putting finishing touched on the Paper and project. The DB is looking good and the call functions are working in the API connecting the front end to the back end to complete the course look-ups that are requested. The paper is coming together very well as we update and correct some of the documentation. Also, the GUI is starting to look beatuiful as we make some last tweaks! | 2015-12-07
Green | Final Presentation | We wrapped coding the the API, GUI, and DB. Finished the Paper and documentation. Created our slides and went over presentation. | Ready to present Foxify! | 2015-12-13